## Sprint
[5 empty] | Week #1 (8 hrs / week) | [6 empty] | Week #2 8 hrs / week) | [6 empty] | Week #3 (8 hrs / week) | [6 empty] | Week #4 (8 hrs / week) | [6 empty] | Week #5 (8 hrs / week) | [6 empty] | Week #6 (8hrs / week) | [6 empty] | Week #7(8hrs / week) | [6 empty] | Week #8 (8 hrs / week) | [6 empty] | Week #9(8hrs / week) | [6 empty] | Week #10 (8 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 32 x 10) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
Cross check your totals here | time axis 2020-02-29 to 2020-05-08
[5 empty] | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | 0 | -9 | -18 | -27 | -36 | -45 | -54 | -63 | -72 | -81 | -90 | -99 | -108 | -117 | 0 | -9 | -18 | -27 | -36 | -45 | -54 | -63 | -72 | -81 | -90 | -99 | -108 | -117 | 0 | -9 | -18 | -27 | -36 | -45 | -54 | -63 | -72 | -81 | -90 | -99 | -108 | -117 | 0
|  |  | 239 |  | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 0 | 4 | 4 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 3 | 0 | 4 | 0 | 4 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 9 | 5 | 2 | 0 | 2 | 0 | 2 | 8 | 8 | 2 | 2 | 6 | 2 | 5 | 2 | 6 | 3 | 4 | 2 | 7 | 1 | 3 | 1 | 0
Business flow planning and Design | Business flow planning and Design | Yashwant | 4 | 4 | 2020-02-29: 1; 2020-03-04: 2; 2020-03-11: 1
| Business flow planning and Design | Krutika | 4 | 4 | 2020-02-29: 1; 2020-03-04: 2; 2020-03-11: 1
| Business flow planning and Design | Chaitanya | 4 | 4 | 2020-02-29: 1; 2020-03-04: 2; 2020-03-11: 1
| Business flow planning and Design | Sathya | 4 | 4 | 2020-02-29: 1; 2020-03-04: 2; 2020-03-11: 1
Backend | Maven Starter code deployment | Yashwant | 4 | 4 | 2020-03-04: 4
| Business logic + Maven dependencies | Chaitanya | 8 | 0
| Web security | Yashwant | 7 | 7 | 2020-04-09: 7
| Driver implementation with login | Yashwant | 10 | 10 | 2020-03-09: 2; 2020-03-12: 3; 2020-03-19: 3; 2020-03-20: 2
| Implementation of Vehicles model | Yashwant | 8 | 8 | 2020-03-23: 4; 2020-03-26: 4
| Implementation of Payment Cards for driver | Yashwant | 10 | 10 | 2020-03-31: 2; 2020-04-02: 2; 2020-04-03: 1; 2020-04-16: 5
| Bug fixing and Refactoring | Yashwant | 5 | 5 | 2020-04-23: 2; 2020-04-30: 2; 2020-05-07: 1
| CORS filter for frontend | Chaitanya | 16 | 0
| Admin model | Chaitanya | 8 | 0
| Driver and DriverCard model + repository | Krutika | 8 | 8 | 2020-03-04: 2; 2020-03-11: 2; 2020-03-17: 2; 2020-03-22: 2
| Vehicle and Location model + repository | Yashwant | 16 | 0
| Reservation model + repository | Krutika | 34 | 34 | 2020-03-26: 4; 2020-04-02: 4; 2020-04-03: 2; 2020-04-05: 4; 2020-04-07: 4; 2020-04-13: 2; 2020-04-15: 3; 2020-04-19: 2; 2020-04-22: 4; 2020-04-26: 2; 2020-04-28: 2; 2020-05-05: 1
| Review model + repository | Krutika | 8 | 8 | 2020-04-17: 2; 2020-04-23: 2; 2020-04-30: 2; 2020-05-02: 1; 2020-05-04: 1
| Test + fix backend APIs | Krutika | 12 | 12 | 2020-04-15: 4; 2020-04-22: 2; 2020-04-23: 2; 2020-04-28: 1; 2020-05-02: 1; 2020-05-04: 2
Frontend | Admin side- Frontend ui for adding vehicles, locations and signin | Sathya | 10 | 10 | 2020-04-22: 2; 2020-04-23: 2; 2020-04-24: 2; 2020-04-25: 2; 2020-04-26: 2
| Signin and Register on User side | Sathya | 4 | 4 | 2020-04-26: 2; 2020-04-27: 2
| User side- profile page, reservations and search functionality integration. | Sathya | 12 | 12 | 2020-04-29: 2; 2020-04-30: 2; 2020-05-01: 2; 2020-05-02: 2; 2020-05-03: 2; 2020-05-04: 2
| Insert your parts | Chaitanya | 16 | 4 | 2020-04-15: 2; 2020-04-21: 2; 2020-04-28: 2; 2020-05-01: 1; 2020-05-04: 1
Fronend + backend Integration | Integration of frontend with backend api's. | Sathya | 8 | 8
|  | Krutika | 8 | 8 | 2020-03-22: 2; 2020-05-04: 1
AWS implementation |  | Chaitanya | 8 | 0 | 2020-05-06: 3
Documentation | Sprint Task sheet | Krutika | 3 | 3
| Project Journal + Core values | Krutika | 3
| UML Diagram | Chaitanya | 4 | 0
| UI Wireframes | ?
| Deployment Diagram | Chaitanya | 4 | 0
250
Team:
Chaitanya Dasari | 8 hours / Week
Yashwant Khade | 8 hours / Week
Sathya Sri | 8 hours / Week
Krutika Katelia | 8 hours / Week
Total Available Hours During Sprint: | 32