## Sprint
[5 empty] | Week #1 (8 hrs / week) | [6 empty] | Week #2 8 hrs / week) | [6 empty] | Week #3 (8 hrs / week) | [6 empty] | Week #4 (8 hrs / week) | [6 empty] | Week #5 (8 hrs / week) | [6 empty] | Week #6 (8hrs / week) | [6 empty] | Week #7(8hrs / week) | [6 empty] | Week #8 (8 hrs / week) | [6 empty] | Week #9(8hrs / week) | [6 empty] | Week #10 (8 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 32 x 10) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
Cross check your totals here | time axis 2020-02-29 to 2020-05-08
[5 empty] | 280 | 276 | 269 | 262 | 255 | 248 | 241 | 234 | 227 | 220 | 213 | 206 | 199 | 192 | 185 | 178 | 171 | 164 | 157 | 150 | 143 | 136 | 129 | 122 | 115 | 108 | 101 | 94 | 87 | 80 | 73 | 66 | 59 | 52 | 45 | 38 | 31 | 24 | 17 | 10 | 3 | -4 | -11 | -18 | -25 | -32 | -39 | -46 | -53 | -60 | -67 | -74 | -81 | -88 | -95 | -102 | -109 | -116 | -123 | -130 | -137 | -144 | -151 | -158 | -165 | -172 | -179 | -186 | -193 | -200
|  |  | 280 |  | 0 | 0 | 2 | 1 | 9 | 1 | 1 | 0 | 0 | 3 | 2 | 1 | 6 | 0 | 0 | 1 | 5 | 2 | 5 | 6 | 2 | 0 | 9 | 4 | 3 | 2 | 13 | 2 | 0 | 9 | 2 | 4 | 1 | 6 | 3 | 0 | 5 | 9 | 2 | 4 | 9 | 0 | 0 | 0 | 3 | 0 | 11 | 3 | 2 | 0 | 2 | 1 | 4 | 13 | 6 | 3 | 2 | 7 | 5 | 8 | 9 | 12 | 9 | 8 | 4 | 11 | 3 | 9 | 5 | 0
Business flow planning and Design | Business flow planning and Design | Yashwant | 1 | 1 | bar: 2020-03-04
| Business flow planning and Design | Krutika | 1 | 1 | bar: 2020-03-04
| Business flow planning and Design | Chaitanya | 1 | 1 | bar: 2020-03-04
| Business flow planning and Design | Sathya | 1 | 1 | bar: 2020-03-04
Backend | Maven Starter code deployment | Yashwant | 4 | 4 | 2020-03-04: 4
| Business logic + Maven dependencies | Chaitanya | 8 | 8 | 2020-03-02: 2; 2020-03-12: 2; 2020-03-16: 2; 2020-03-22: 2
| Web security | Yashwant | 13 | 13 | 2020-03-18: 2; 2020-03-25: 2; 2020-03-30: 2; 2020-04-09: 7
| Driver implementation with login | Yashwant | 10 | 10 | 2020-03-09: 2; 2020-03-12: 2; 2020-03-16: 1; 2020-03-19: 3; 2020-03-20: 2
| Implementation of Vehicles model | Yashwant | 8 | 8 | 2020-03-23: 4; 2020-03-26: 4
| Implementation of Payment Cards for driver | Yashwant | 8 | 8 | 2020-03-31: 2; 2020-04-02: 2; 2020-04-03: 1; 2020-04-16: 3
| Bug fixing and Refactoring | Yashwant | 12 | 12 | 2020-04-15: 2; 2020-04-20: 1; 2020-04-23: 1; 2020-04-29: 1; 2020-04-30: 2; 2020-05-06: 4; 2020-05-07: 1
| CORS filter for frontend | Chaitanya | 16 | 16 | 2020-03-05: 1; 2020-03-09: 1; 2020-03-15: 1; 2020-03-18: 2; 2020-03-22: 3; 2020-03-27: 2; 2020-03-31: 2; 2020-04-05: 1; 2020-04-06: 3
| Admin model | Chaitanya | 8 | 8 | 2020-03-06: 1; 2020-03-12: 2; 2020-03-16: 2; 2020-03-26: 1; 2020-03-29: 2
| Driver and DriverCard model + repository | Krutika | 6 | 6 | 2020-03-04: 1; 2020-03-11: 1; 2020-03-17: 2; 2020-03-22: 2
| Vehicle and Location model + repository | Yashwant | 14 | 14 | 2020-03-19: 3; 2020-03-24: 3; 2020-03-29: 4; 2020-04-06: 4
| Reservation model + repository | Krutika | 30 | 30 | 2020-03-26: 4; 2020-04-02: 4; 2020-04-03: 2; 2020-04-05: 2; 2020-04-07: 2; 2020-04-13: 2; 2020-04-15: 3; 2020-04-19: 2; 2020-04-22: 4; 2020-04-26: 2; 2020-04-28: 2; 2020-05-05: 1
| Review model + repository | Krutika | 8 | 8 | 2020-04-17: 2; 2020-04-23: 2; 2020-04-30: 2; 2020-05-02: 1; 2020-05-04: 1
| Test + fix backend APIs | Krutika | 12 | 12 | 2020-04-15: 4; 2020-04-22: 2; 2020-04-23: 2; 2020-04-28: 1; 2020-05-02: 1; 2020-05-04: 2
Frontend | Admin side- Frontend ui for adding vehicles, locations and signin | Sathya | 15 | 15 | 2020-04-22: 2; 2020-04-23: 1; 2020-04-24: 1; 2020-04-26: 2; 2020-04-27: 2; 2020-04-28: 1; 2020-04-29: 2; 2020-04-30: 2; 2020-05-01: 2
| Signin and Register on User side | Sathya | 16 | 16 | 2020-04-21: 2; 2020-04-22: 2; 2020-04-26: 1; 2020-04-27: 1; 2020-05-02: 2; 2020-05-03: 2; 2020-05-04: 2; 2020-05-05: 2; 2020-05-06: 2
| User side- profile page, reservations and search functionality integration. | Sathya | 18 | 18 | 2020-04-29: 4; 2020-04-30: 4; 2020-05-01: 4; 2020-05-02: 2; 2020-05-03: 2; 2020-05-04: 2
| UI workflow and integration | Chaitanya | 19 | 19 | 2020-03-03: 1; 2020-03-10: 2; 2020-03-18: 1; 2020-03-26: 2; 2020-03-29: 3; 2020-04-09: 2; 2020-04-15: 2; 2020-04-21: 2; 2020-04-28: 2; 2020-05-01: 1; 2020-05-04: 1
Fronend + backend Integration | Integration of frontend with backend api's. | Sathya | 20 | 20 | 2020-04-22: 2; 2020-04-24: 2; 2020-04-25: 2; 2020-04-26: 2; 2020-04-27: 2; 2020-04-28: 2; 2020-04-29: 2; 2020-04-30: 2; 2020-05-01: 2; 2020-05-02: 2
| Integration of frontend with backend api's. | Krutika | 8 | 8 | 2020-03-22: 2; 2020-03-26: 2; 2020-04-01: 1; 2020-04-05: 2; 2020-05-04: 1
AWS implementation | AWS Implementation | Chaitanya | 8 | 8 | 2020-04-06: 2; 2020-04-13: 1; 2020-05-06: 3; 2020-05-07: 2
Documentation | Sprint Task sheet | Krutika | 3 | 3 | 2020-04-22: 1; 2020-05-07: 2
| Project Journal + Core values | Krutika | 2 | 2 | 2020-05-04: 2
| UML Diagram | Chaitanya | 4 | 4 | 2020-04-08: 4
| UI Wireframes | Chaitanya | 2 | 2 | 2020-05-07: 2
| Deployment Diagram | Chaitanya | 4 | 4 | 2020-04-15: 4
280
Team:
Chaitanya Dasari | 7 hours / Week
Yashwant Khade | 7 hours / Week
Sathya Sri | 7 hours / Week
Krutika Katelia | 7 hours / Week
Total Available Hours During Sprint: | 28